## Agenda
FINANCE COMMITTEE MEETING 7:00 PM
2010-03-16
PRESENT ABSENT
Robert Trask, Chairman (2010) | X
Tim Fila, Vice Chairmen (2010) | X
Stephen Burke, Secretary (2012) | X
Joe Dattilo, L & P (2010) | X
Skip Raleigh, L&P (2011) | X
Judy Fletcher (2011) | X
Kurt Lynn (2012) | X
James Devens, Board of Directors |  | X
Ron Wilson, Operations Manager | X
Guests:
1. Roll Call
2. Approval of Minutes | Motion | Second |  | Approved ?
| Lynn | Fila |  | unanimous
3. Approval of Agenda | Motion | Second |  | Approved ?
as modified | Fila | Fletcher |  | unanimous
4. New Business | Motion | Second |  | Approved ?
a. Bids Green Mower | Lynn | Fila |  | unanimous
motion to approve bid for approx $22K for demo John Deere mower from ERB Turf Equipment
b. Bids Security Camera | Motion | Second |  | Approved?
| Fila | Fletcher |  | unanimous
motion to approve approx $15K bid from Interface - Option #1 contingent on 1 yr warrantee.
Finance discussed this justification of this expense based on past vandalism and theft - also improved service at the bar.
c. Bids Docks | Motion | Second |  | Approved?
| Fila | Raleigh |  | unanimous
motion to approve C&J's bid for approx $5100 for additional docks at the large dam
CA to request installation no later than 5/28/10.
d. Electric Cost
Robert Trask suggested Ron to contact the Water District to see if we can install a sub-meter on the water line.
Ron reported that main increase was due to power company rate increases.
e. Silt Removal Cost
$160K on silt removal and lake cleanup
|  | breakdown: | 12K | weed kill in small lake
|  |  | 5K | fuel spill deductible
|  |  | 8K | tree grinder
|  |  | 5K | power at Duello
|  |  | 120K | heavy equipment at Duello
Ron estimates 30K - 40K cubic yards have been removed by private contractors. This leaves approx 250K cubic yards to be removed.
Going forward the CA will pay for a high lift loader and bulldozer by the hour to move silt 1/4 mile from the rear to the front of the yard.
Also looking into possibility of getting bids to remove silt completely.
f. RFQ / Bid Approval Process | Motion | Second |  | Approved ?
| Lynn | Dattilo |  | Defeated 4-2
motion to request the CA Employees to issue a informal RFQ on capital bids for review by Finance before submittal.
Finance agreed to review different processes from outside companies and attempt to define a RFQ Process with Ron.
Steve Burke will obtain copies of different procedures from multiple companies to start this process.
g. Board Direction | Joe Dattilo requested the BOD to give direction for this committee in 2010.
h. Accrual Question on special election
Committee would like clarification of Botz and Deal expenses related to fees for questions from the special election.
Motion to instruct Election Judge Auditing Firm to steer questions around elections back to the CA office if these will result in increased cost to the CA membership.
| Motion | Second |  | Approved ?
| Lynn | Fletcher |  | unanimous
5. Old Business
a. Investments | Tim Fila would like to know when the $250K limit will be lowered to $100K by the Federal Govt - Ron will advise.
Tim Fila requested that we get a quote for all Ca financial services from banks that specialize in Community Association business.
6. Adjournment | Motion | Second |  | Approved ?
| Fila | Fletcher |  | unanimous