Engineering and Facilities Committee Meeting Minutes

Monday – Aug 6, 2012 7:00 PM

# Committee Members				Present             	Absent

Kurt Lynn – Chairman **			___x___            	______

Jim Sharkey– Vice Chairman			___x___	______

Clint Moor -Secretary                                       	__x____             	______

Norm Cibula					______		___x___

Rich Buehner					__x____             	______

Pat Mongoven					______          	__x____

Ed Ketterer					__x____	______

Ben Cooper					__x____	______

Lynn Partington					__x____	______

** Finance Committee Members from E&F

#### Quorum? Yes

CA Representatives

Joan Tobin, CA Board 		                        	__x____               _______

Donnie Harrell, CA Staff                                         	__x____               _______

Ron Wilson, CA Manager                                 	__x____          	_______

## AGENDA

- Roll Call

- Recognized Guests  - Doug Tiemann, PRS; CA Board members Wayne W, Jerry K, Faye S, Tom S,

- Approval of Minutes  - No minutes available

- Approval of Agenda – Agenda sequence changed to address Dredging first.

- Report from the Board of Directors Meeting

- Report from Staff –Included in items below.

- Report from Lakes and Parks -None

- Report from Finance Committee - None

- Old Business –Jeff Point work will go out for bid this month. The bid will include all infrastructure.

- New Business

  - Dredge, Dredge, Dredge

    - Duello Road Silt Basin Status – Surveyed area is 17 acres. Need to raise berm to 522 ft ASL; Berm is at 522 but needs to be fixed to insure it wont fail during dredge. Bottom now is between 510-512, so a depth of 10-12 feet means it will hold 290,000cu yds. To get 30% spare capacity means we need 330,000cu yds . Raising the berm 1 ft provides about 30,000 cu yds per ft of added height. Also a water quality check will be required which means a settlement basin is needed. Water exiting settlement basin will flow back to Peruque Creek. Duello basin needs added cells or flow control to aid in siltation.

    - Cove Silt Status for All Coves Inspected –PRS has surveyed Dauphine Cove 3 times recently, the latest in June 2012. Using 500.8 ASL as the reference (low point on dam spillway) for lake water level, then dredging to achieve 8 feet depth would require a bottom level after dredging of 492 ASL. Estimated material to be dredged would be 253,000 cu yds. This cove is defined as extending from the highway bridge to Sta 38, or 3800 feet. Dregde would have to pump material approx 7000 ft to 10,000ft. How effective is dredging? Last dregdging operation got approx 90% of estimate. A post-dredge survey will be used to est cu yds removed.

-Plans call for Villa Cove, Regatta and Lakewood Coves to be dredged to 492 ASL also. The material estimated to be removed is 30,140 cu yds total; Villa 13,000 cu yds, Regatta 13,540 cu yds, Lakewood 3600 cu yds. This material would be pumped behind the main dam on the big lake where detention cells have been built before. Pump distance is 8000 ft, 4500 ft and 5600 ft respectively.

-Below main dam a 3 cell pond design would store 42,000 cu yds if its 8 ft deep and have 10 ft wide berms. On June 22, a request was sent to Corp of Engr, Jennifer Brown has been assigned; Work also requires City of LSL grading permits for both sites plus moving of 15,000 cu yds. A DNR land disturbance permit is required. Currently DNR has previously issued a dredge permit for 2008-2013. Water quality for discharge water is 1.5 ppm.

-MOTION: Kurt L made and Lynn P seconded a motion to have PRS survey at Regatta Cove the manholes and lateral elevations and insure that the documented elevations of laterals and manholes argree with the data being used for the dredging. It must support the possibility of dredging down to 492 ASL or define a different elevation for safe dredging.Motion passed unan.

-MOTION: Recommend that if we dredge Dauphine Cove, we dredge Lakewood, Regatta and Villa Cove to 492 Depthor whatever is determined to clear sewer and lateral lines. (Villa was dredged with Dauphine last time; all others have only been mech dredged.)

-MOTION: Recommend staff work with PWSD #2 to locate sewer line mains and laterals in Lakewood and Regatta Coves.

-MOTION: Recommend we contract with a sonic measuring company to accurately map depth and location of sewer lines and laterals in Lakewood and Regatta coves.

-MOTION: Recommend that PRS integrate data into an analysis to show it if they support each other and that dredging is feasible.

-MOTION: Recommend the we plan to actively dry basin after dredging and put in infrastructure for dewatering system before dredging begins.

-MOTION: Recommend that Staff and PRS (if necessary) investigate the change of bottom of the lake beyond Sta 38 (3800 ft)to find existing natural bottom ,i.e. 492 ASL or other elevation so the 492 level can be sloped to meet existing bottom if desired.

-MOTION: Recommend we dredge from Sta3800 to Sta 0 (at Hwy 40 bridge)  to nominal depth of 492ASL which equates to 253,000 cu yds.

NOTE: all motions made by Kurt L and seconded by Lynn P. All passed unanimously.

    - Sewer Lines and Other Utilities in Coves  - See notes above

    - Dredging Bid Status – Bid packages are available to be sent out. Magruder and two others have been solicited. Specs done for dredge, specs done for basin below dam and for repair on Duello Road basin

  - Tennis Court Pole Breakout on South Side of Concrete – Not a structural problem; cosmetic repair required.

- General Discussion / Comments

-Bids are out for small lake dam (wall) work and for stairs on Lundi Ct.

-Electrical Inspections on private docks- There are 225 docks on the big lake; We need rules, who should do inspections, etc. Plans are being developed to carry this out.

- Small Lake – Clermont Cove – Estimate is $4500 to do a mechanical dredge. It was tabled until Large lake dredge has begun

- Jetty –Found new Engr co , seems to be a good company ( Intuition & Logic). In 30 -60 days may have new ideas  and costs available. They need an estimate of debris we expect to catch.

- Adjournment – Rich made a motion to adjourn, Lynn seconded. All approved