Engineering and Facilities Committee Meeting Minutes

Monday – Dec 5, 2011 7:00 PM

# Committee Members				Present             	Absent

Kurt Lynn – Chairman **			___x___            	______

Jim Sharkey– Vice Chairman			___x___	______

Norm Cibula					___x___	______

Rich Buehner                                      		______             	___x___

Pat Mongoven					______          	__x____

Ed Ketterer					__x____	______

Tom DeLong** 					______		__x____

Clint Moor - Secretary  	`			___x___             	______

Lynn Partington					___x___	______

** Finance Committee Members from E&F

#### Quorum ?  Yes

CA Representatives

Joan Tobin, CA Board 		                        	__x____               _______

Donnie Harrell, CA Staff                                         	__x____               _______

Steve Probst, Project Manager                                 	______          	__x_____

Ron Wilson, CA					___x___	_______

## AGENDA

Premeeting – Jefferson Point Ad Hoc Committee

- Roll Call

- Recognized Guests

- Approval of Minutes – Motion to approve Minutes of Nov mtg by Norm, second by Ed . Unan

- Approval of Agenda – Jim made motion to add four items to agenda in New Bus; D – Expiration of Terms; E – 2012 Officers; F New Members ; G – Lundi Path Project.; second by Clint; passed unan.

- Report from the Board of Directors Meeting – Everything at Board mtg passed except Jeff Pt; all committees appd Jeff Pt except E & F (must do at next mtg); Bd wants to interview all people who are candidates for E&F committee; Discussion of storage space for clubs.

- Report from Staff –Paris Cove dredge pumping water via 1 ½ in pipeline.  Approx 65,000 Cu Yds dirt loaded out in last 2 years.

- Report from Lakes and Parks – wants to add big trees and irrigation to Jeff Pt

- Report from Finance Committee- Wants Land Use Engr to design or review Jeff Pt to insure “best” use of land at Jeff Pt.

- Old Business

  - Duello Road Silt Basin Levee Status – Done loading dirt for the year;2900+/- loads for the year and Norvel took 8300 Cu Yds; Need one more year and most all detention area will be empty; Will start levee work after completed; Summary – 14 acres mostly empty, 7 acres still full ( never emptied in past); Ready to dredge as planned.

- New Business

  - Dauphine Dredge Status – Parts obtained and dredge now working;  approx 6 ft deep inside dredge area; contractor thinks approx 3500 cu yds moved; depth of dredged area will be checked; work to continue thru Dec 2011.

  - Paris Cove Dredge Status – A new dredge is working now;  Dredge is trash pump with 1 ½ in pipeline; meeting with sewer company Dec 6; Marking sewer locations on 12/6 and providing info to dredge operator.

  - Jefferson Point Recommendation based on Ad Hoc Committee –Jim made motion to approve Concept 11 plan ( presented to Bd) as presented by Cochran Engr along with the budget to support it; second by Lynn; appd unan  Motion by Jim to approved the schedule below and send it to Bd as recommendation; second by Ed; appd unan.  See Sched at bottom of minutes

  - Term Limits – Norm’s term expires in 2011; Motion by Clint, sec by Jim to extend Norm’s term for three more years. Appd unan.

  - Officers – Motion by Norm to recommend Kurt Lynn as Chairman, Jim Sharkey as Vice Chair and Clint Moor as Secretary. Lynn P seconded. Appd unan.

  - New Members – Ben Cooper’s resume has been received for consideration. Kurt to check on number of members and interest of members to continue before making recommendations.

  - Lundi Ct Path Project- Donnie brought a plat of area; some discussion held on path type, elevation, etc. It is over 100 ft from curb to level area on common ground; in one 72 ft section of path, fall is 18 ft; this steep terrain will require steps; Donnie to bring more info and potential layouts next month. Plans should add electric so it can be added to docks serviced.

- General Discussion / Comments -  General discussions on Jeff Pt and Lundi Ct path

- Adjournment – Motion by Lynn P to adj; appd unan

Suggested Schedule for Jefferson Point

Year 1 (2012)   Gate, Water line, Electric, Bathrooms

Year 2 (2013)   Pavilion, Picnic Tables, Benches

Year 3 ( 2014)  Fire Pit, Beach, Outdoor shower, Maintenance, Storage area

Year 4 (2015)   Sidewalks, Roadwork incl maintenance road and Contractors Material storage

Year 5 (2016)   Landscaping, Lighting, Sprinklers, Parking and road paving.

Year 6 (2017)   Things we did not get done